## Site Location
# | Sites | Building Size | Vendor | Location | First Recv I/O Check | Frist Receive | First Ship
1 | BFL1 | 640K | INTL | Bakersfield, CA | 2020-07-19 | 2020-08-09 | 2020-08-16
2 | MKE2 | 640K | INTL | Oak Creek, WI | 2020-07-19 | 2020-08-16 | 2020-08-23
3 | AKC1 | 640K | INTL | Akron, OH | 2020-08-02 | 2020-08-16 | 2020-08-23
4 | ATL2 | 640K | DEM | Stone Mountain, GA | 2020-08-02 | 2020-08-23 | 2020-08-30
5 | PCW1 | 640K | INTL | ROSSFORD, OH | 2020-08-02 | 2020-08-30 | 2020-09-06
6 | BOI2 | 640K | INTL | Nampa, Idaho | 2020-08-30 | 2020-09-13 | 2020-09-20
7 | DSM5 | 640K | INTL | #N/A | 2020-09-27 | 2020-10-11 | 2020-10-18

## Sch w-Intl - Siemens
# | Sites | March | April | May | June | July | August | September | October | November | December | January
1 | MKE2 | April: PO 4/17; July: 7/17 - 8/5 | First Receive i/O Check
7/26 -8/17
| MKE2 | July: 7/19 - 8/17
2 | ATL2 | August: 8/7 - 8/26 | Siemens
|  | August: Dematic | Intl
| ATL2 | August: 8/2 - 8/23
3 | BOI2 | August: 8/21 - 9/9
8/10 - 8/31
| BOI2 | August: 8/30 - 9/13
4 | DSM5 | September: 9/4 - 9/23
8/10 - 8/31
| DSM5 | September: 9/27 - 10/11
5 | AKC1 | October: 10/5 - 10/28
8/2 - 8/25
| AKC1 | August: 8/2 - 8/16
6 | BFL1 | September: 9/18 - 10/7
Intellligrated
7/19 - 8/9
7 | PCW1 | October: 10/16 - 11/11
8/2 - 8/25
| PCW1 | August: 8/2 - 8/30
* each receive line will be installed in sequence one at the time.
# | Sites | Building Size | Vendor | First Recv I/O Check | Frist Receive | First Ship | Siemens Proposal | Intelligrated Dematic | 30 Destackers Available
1 | MKE2 | 640K | INTL | 2020-07-19 | 2020-08-16 | 2020-08-23 | 7/17 - 7/31 | 7/26 - 8/17 | 2020-07-17
2 | ATL2 | 640K | DEM | 2020-08-02 | 2020-08-23 | 2020-08-30 | 8/7 - 8/21 | - | 2020-08-07
3 | BOI2 | 640K | INTL | 2020-08-30 | 2020-09-13 | 2020-09-20 | 8/21 -9/4 | 8/10 - 8/31 | 2020-08-21
4 | DSM5 | 640K | INTL | 2020-09-27 | 2020-10-11 | 2020-10-18 | 9/4 - 9/18 | 8/17 - 9/7 | 2020-09-18
5 | AKC1 | 640K | INTL | 2020-08-02 | 2020-08-16 | 2020-08-23 | 10/2 - 10/23 | 8/2 - 8/25 | 2020-10-02
6 | BFL1 | 640K | INTL | 2020-07-19 | 2020-08-09 | 2020-08-16 | 9/18 -10/2 | - | 2020-09-04
7 | PCW1 | 640K | INTL | 2020-08-02 | 2020-08-30 | 2020-09-06 | 10/16 - 11/11 | 8/2 - 8/25 | 2020-10-16

## Install Sch Covid19 Impact
# | *Sites | copied to NACF-AE | Building Size | Vendor | First Recv IQ/OQ | First Receive IQ/OQ w/covid19 | Frist Receive | First Receive w/covid19 | First Ship | First Ship w/covid19 | Destackers Available | Siemens Install Proposal | Intelligrated Dematic | April | May | June | July | August | September | October | November | December | January
| ATL2 | [12 empty] | April: PO 4/17; July: 7/17 - 8/5 | Siemens
1 |  | y | 640K | DEM | 2020-08-02 | 2020-08-23 | 2020-08-23 | 2020-09-06 | 2020-08-30 | 2020-09-27 | 2020-08-07 | 8/7 - 8/21 | - | August: Dematic | Intl
| ATL2 | [10 empty] | 7/17 - 7/31 |  | August: 8/23 - 9/6 | Dematic
| MKE2 | [12 empty] | August: 8/7 - 8/26 | First Receive i/O Check
2 |  | y | 640K | INTL | 2020-07-19 | 2020-08-30 | 2020-08-16 | 2020-09-13 | 2020-08-23 | 2020-10-04 | 2020-07-17 | 7/17 - 7/31 | 7/26 - 8/17 | July: 7/26 -8/17
| MKE2 | [10 empty] | 8/7 - 8/21 |  | August: 8/30 - 9/13
| AKC1 | [12 empty] | August: 8/21 - 9/9
3 |  | y | 640K | INTL | 2020-08-02 | 2020-09-06 | 2020-08-16 | 2020-09-20 | 2020-08-23 | 2020-09-27 | 2020-10-02 | 10/2 - 10/23 | 8/2 - 8/25 | August: 8/2 - 8/25
| AKC1 | [10 empty] | 8/21 - 9/4 |  | September: 9/6 - 9/20
| PCW1 | [12 empty] | September: 9/4 - 9/23
4 |  | y | 640K | INTL | 2020-08-02 | 2020-09-13 | 2020-08-30 | 2020-09-27 | 2020-09-06 | 2020-10-11 | 2020-10-16 | 10/16 - 11/11 | 8/2 - 8/25 | August: 8/2 - 8/25
| PCW1 | [10 empty] | 9/1 - 9/18 |  | September: 9/13 - 9/27
| BOI2 | [12 empty] | September: 9/18 - 10/7
5 |  | y | 640K | INTL | 2020-08-30 | 2020-10-11 | 2020-09-13 | 2020-10-25 | 2020-09-20 | 2020-11-15 | 2020-08-21 | 8/21 -9/4 | 8/10 - 8/31 | August: 8/10 - 8/31
| BOI2 | [10 empty] | 9/18 - 10/2 |  | October: 10/11 - 10/25
| DSM5 | [12 empty] | October: 10/16 - 11/11
6 |  |  | 640K | INTL | 2020-09-27 | 2020-11-08 | 2020-10-11 | 2020-11-22 | 2020-10-18 | 2020-12-13 | 2020-09-18 | 9/4 - 9/18 | 8/17 - 9/7 | August: 8/10 - 8/31
| DSM5 | [10 empty] | 10/16 - 11/11 |  | November: 11/8 - 11/22
| BFL1 | [12 empty] | October: TBD
7 |  |  | 640K | INTL | 2020-07-19 | 2020-07-19 | 2020-08-09 | 2020-08-09 | 2020-08-16 | 2020-08-16 | 2020-09-04 | 9/18 -10/2 | - | October: TBD
[12 empty] | 10/2 - 10/23 |  | July: 7/19 - 8/9
**PSP1
8 |  |  | 640K | INTL | 2020-08-24 | 2020-08-24 | 2020-09-06 | 2020-09-06 | 2020-09-13 | 2020-09-13 |  | 9/18 -10/2 | -
[12 empty] | 10/2 - 10/23 |  | August: 8/24 - 9/6
***JAX2
9 |  |  | 640K | INTL | 2020-07-19 | 2020-07-19 | 2020-08-09 | 2020-08-09 | 2020-08-16 | 2020-08-16 | 2020-09-04 | 9/18 -10/2 | -
10/2 - 10/23
* To all sites each receive line will be installed in sequence one at the time.
**
***

## Siemens Mftg plan
|  |  | Count Weeks |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41
Friday: MFG Completion Dates/Ship | time axis 2020-03-13 to 2021-01-22
[23 empty] | 1 |  |  | 2 | 1 |  |  |  |  | 1 | 1
2 B
|  |  | MFG Rework 4, Expedite, Buy New Parts, Lead Time | 2020-05-22: Lead Time to Qty
| Production Modules | 15 Modules a Week | Up Grade 4 Units in FG and Ramp to Production Rate | [11 empty] | 2 | 4 | 6 | 8 | 8 | 6 | 8 | 10 | 15 | 15 | 9 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 9 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 5 | 360 | 12
3 A |  |  | Eng Resume , Complete ALL Changes and Release in SAP | bar: 2020-04-24 to 2020-08-21
MFG Rework, Expedite, Buy New Parts | bar: 2020-05-22 to 2020-06-26
| Max Number | 20 Modules a Week | Up Grade 4 Units in FG and build the Remaining 40, Then New Production | 2020-07-03: 2; 2020-07-10: 2; 2020-07-17: 4; 2020-07-24: 6; 2020-07-31: 8; 2020-08-07: 8; 2020-08-14: 6; 2020-08-21: 8; 2020-08-28: 10; 2020-09-04: 15; 2020-09-11: 20; 2020-09-18: 20; 2020-09-25: 20; 2020-10-02: 20; 2020-10-09: 20; 2020-10-16: 20; 2020-10-23: 12; 2020-10-30: 20; 2020-11-06: 20; 2020-11-13: 20; 2020-11-20: 20; 2020-11-27: 20; 2020-12-04: 20; 2020-12-11: 20; 2021-01-01: 341; 2021-01-08: 11.3667
3 B |  |  | Eng Resume , Complete ALL Changes and Release in SAP | bar: 2020-03-13 to 2020-07-17
MFG Rework, Expedite, Buy New Parts | bar: 2020-04-17 to 2020-05-22
| Max Number | 20 Modules a Week | Up Grade 4 Units in FG and build the Remaining 40, Then New Production | [10 empty] | 2 | 2 | 4 | 6 | 8 | 8 | 6 | 8 | 10 | 15 | 20 | 12 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 12 | 20 | 20 | 20 | 20 | 20 | 20 | 20 |  |  | 433 | 14.4333
|  |  | MKE2 | 2020-04-17: Site 1; 2020-06-05: 2; 2020-06-12: 6; 2020-06-19: 12; 2020-06-26: 20; 2020-07-03: 28; 2020-07-10: 34
|  |  | ATL2 | 2020-04-17: Site 2; 2020-07-10: 4; 2020-07-17: 12; 2020-07-24: 22; 2020-07-31: 37
|  |  | BOI2 | 2020-04-17: Site 3; 2020-07-31: 7; 2020-08-07: 22; 2020-08-14: 31
|  |  | DSM5 | 2020-04-17: Site 4; 2020-08-14: 1; 2020-08-21: 16; 2020-08-28: 31
|  |  | BFL1 | 2020-04-17: Site 5; 2020-08-28: 1; 2020-09-04: 16; 2020-09-11: 31
|  |  | AKC1 | 2020-04-17: Site 6; 2020-09-11: 1; 2020-09-18: 16; 2020-09-25: 31
|  |  | PCW1 | 2020-04-17: Site 7; 2020-09-25: 1; 2020-10-02: 16; 2020-10-09: 31
[8 empty] | Site 8 | [24 empty] | 1 | 16 | 25 | 40
[8 empty] | Site 9 | [27 empty] | 10 | 25 | 40
[8 empty] | Site 10 | [29 empty] | 10 | 25 | 40
[8 empty] | Site 11 | [31 empty] | 10 | 25 | 40
[8 empty] | Site 12 | [33 empty] | 10 | 25 | 30
+41:4129:4729:54
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55
Trunkline Ehancement & Powered Spur | time axis 2020-02-17 to 2021-04-05
Amazon RFP Received | bar: 2020-02-17
Amazon / Production Contract Award | bar: 2020-03-16
Engieering / Design Freeze
|  |  | Material Lead Time | 2020-05-18: 10 - week Lead time
Prep for shipping Site ACY1
|  |  | Install @ Site ACY1 (3wks ea Line) | 2020-07-20: 1; 2020-08-10: 2; 2020-08-31: 3
System Testing for Acceptance 2wks | bar: 2020-09-14 to 2020-09-21
ACY1 Acceptance | bar: 2020-09-28
Prep for shipping Site OKC1
|  |  | Install @ Site OKC1 (3wks ea Line) | 2020-08-17: 1; 2020-09-07: 2; 2020-09-28: 3
System Testing for Acceptance 4wks | bar: 2020-10-12 to 2020-10-19
OKC1 Acceptance | bar: 2020-10-26
Peak Break | bar: 2020-11-02 to 2020-12-28
Prep for shipping Site TUL2
|  |  | Install @ Site TUL2 (3wks ea Line) | 2021-01-18: 1; 2021-02-08: 2; 2021-03-01: 3
System Testing for Acceptance 4wks | bar: 2021-03-15 to 2021-03-22
TUL2 Acceptance | bar: 2021-03-29
Prep for shipping Site CLT4
|  |  | Install @ Site CLT4 (3wks ea Line) | 2021-01-18: 1; 2021-02-08: 2; 2021-03-01: 3
System Testing for Acceptance 4wks | bar: 2021-03-15 to 2021-03-22
CLT4 Acceptance | bar: 2021-03-29
[50 empty] | 20 |  |  | 20 |  |  | 20
| Color Legend |  | MKE2 install 7/17-7/31 ----- Amazon FR 7/19 Launch 8/16
| SO Load/Prod LT (14Wks) |  | ATL2 install 8/7-8/21----- Amazon FR 8/2 Launch 8/23
| Engineering Release SAP |  | BOI2 install 8/21-9/4----- Amazon FR 8/30 Launch 9/27
| RWK, Expedite New |  | DSM5 install 9/4-9/18----- Amazon FR 9/27 Launch 10/4
| Build Existing Stock |  | BFL1 install 9/18-10/2----- Amazon FR 7/19 Launch 7/26
| Short Holiday Wk |  | AKC1 install 10/2-10/16----- Amazon FR 8/2 Launch 8/16
| No Fill, New Series Prod |  | PCW1 install 10/16-10/30----- Amazon FR 8/2 Launch 8/30
Contract Award: Go
[46 empty] | 2020-02-19 | 2020-05-19
Ship/Arrive on site

## Covid19 Impact
# | Sites | Building Size | Vendor | First Recv IQ/OQ | First Receive IQ/OQ w/covid19 | Frist Receive | First Receive w/covid19 | First Ship | First Ship w/covid19 | Destackers Available | Siemens Install Proposal | Intelligrated Dematic
1 | MKE2 | 640K | INTL | 2020-07-19 | 2020-08-30 | 2020-08-16 | 2020-09-13 | 2020-08-23 | 2020-10-04 | 2020-07-17 | 7/17 - 7/31 | 7/26 - 8/17
2 | ATL2 | 640K | DEM | 2020-08-02 | 2020-08-23 | 2020-08-23 | 2020-09-06 | 2020-08-30 | 2020-09-27 | 2020-08-07 | 8/7 - 8/21 | -
3 | BOI2 | 640K | INTL | 2020-08-30 | 2020-10-11 | 2020-09-13 | 2020-10-25 | 2020-09-20 | 2020-11-15 | 2020-08-21 | 8/21 -9/4 | 8/10 - 8/31
4 | DSM5 | 640K | INTL | 2020-09-27 | 2020-11-08 | 2020-10-11 | 2020-11-22 | 2020-10-18 | 2020-12-13 | 2020-09-18 | 9/4 - 9/18 | 8/17 - 9/7
5 | AKC1 | 640K | INTL | 2020-08-02 | 2020-09-06 | 2020-08-16 | 2020-09-20 | 2020-08-23 | 2020-09-27 | 2020-10-02 | 10/2 - 10/23 | 8/2 - 8/25
6 | BFL1 | 640K | INTL | 2020-07-19 | 2020-07-19 | 2020-08-09 | 2020-08-09 | 2020-08-16 | 2020-08-16 | 2020-09-04 | 9/18 -10/2 | -
7 | PCW1 | 640K | INTL | 2020-08-02 | 2020-09-13 | 2020-08-30 | 2020-09-27 | 2020-09-06 | 2020-10-11 | 2020-10-16 | 10/16 - 11/11 | 8/2 - 8/25